## Slide 1
Kick-off meeting
Claudio Maria Vitali
WP 5. Monitoring and evaluation
Rome, 21th-22th June 2018
E.QU.A.L.
Enhancing Qualification of Adult Learners
through the implementation of Upskilling pathways
EaSI programme – Awareness-raising activities in Member States on “Upskilling Pathways: New Opportunities for Adults”
Call for proposals VP/2017/011
EUROPEAN COMMISSION
DG Employment, Social Affairs and Inclusion

## Slide 2
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
2
OVERALL DURATION | FROM/TO | PACKAGE LEADER
18 MONTHS | 1 APRIL 2018 30 SEPTEMBER 2019 | INAPP
AIMS
1. To guarantee quality, efficacy and efficiency to project activities implementation. 2. To ensure the achievement of fixed goals and aims. 3. To monitor and evaluate the conformity between planned and realised, during the project implementing process. 4. To guarantee the regular check of project process and outcomes, also with respect to project b budget cash flow. 5. To work out and share modalities, indicators, parameters for the quality check and related tools to collect and analyse qualitative and qualitative data. 6. To assess quality of project outputs and outcomes (relevance, utility, transferability, usability) on the side of both partnership members (internal assessment/self-evaluation) and an external expert.
Notes: Regarding the share of population with either less than primary or primary and lower secondary education (ISCED levels 0-2) Italy ranks 4th with 40.1%, above both the EU (23.5%) average.
Italy has stayed in the same position since 2006, but has improved by 8.6 percentage points (p.p.) since. Concerning the share of the population with either upper secondary or post-secondary non-tertiary education (ISCED levels 3-4) Italy ranks 18th with 42.3%. This figure is slightly below the EU (46.5%) average, but it does represent an increase in comparison to the 38.4% rate registered in 2006.
European Commission, Summary of the Partnership Agreement for Italy, 2014-2020, 2014. Available at: https://ec.europa.eu/info/sites/info/files/partnership-agreement-italy-summary-oct2014_en.pdf
Italy trails only Malta (56.5%), Portugal, and Spain in this ranking (latest data: 2015).

## Slide 3
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
3
ACTIVITIES
Work out of Monitoring and evaluation Plan, including project milestones and deliverables related. Work out of formats to record and survey qualitative and quantitative data and information: questionnaires, reports, minutes addressed to partnership only; evaluation/observation questionnaires addressed to project beneficiaries and project staff involved in the transfer actions; tools for the regular check of project cash flow. Realisation of periodical desk analysis (every 4 months ). Submitting to all partners semi-structured grids/questionnaires aimed at collecting information on specific check areas: activities realised and in progress, timings, outcomes achieved, problems faced and solutions found. In this way it will be possible to monitor implementation conformity and record analytical information. Periodical record of financial data (every 3 months). The project cash flow is a relevant aspect to be under regular control, since it is strictly linked to the production process. Periodical monitoring allows the partnership to identify possible wastes and reserves which may negatively affect the regular implementation process. The recording of these data is also necessary to work out the Project Interim and Final Reports to be submitted to the EU Commission.

## Slide 4
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
4
ACTIVITIES
Production of 2 Monitoring Reports (interim and Final, IT/EN), assessing the project work in progress and outcomes achieved, so as to identify arrangements to be applied to the workplan and analyse – in terms of efficiency, efficacy and relevance – project interim and final outcomes and the impact (sustainability and transferability) produced on target groups/contexts Reports shall include the project risk assessment with respect to: budget, activities, outputs (per WP), process timings. Also in this case, Reports are functional to work out the Project Interim and Final Reports to be submitted to the CE Production of 1 Final report (overall external evaluation) (EN/IT)

## Slide 5
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
5
OUTPUTS
Monitoring and evaluation Plan + FORMATS AND TOOLS (IT/EN). Risk Assessment Chart (EN/IT). 2 monitoring Reports (interim and Final) (IT/EN). 1 Final evaluation report (EN/IT).

## Slide 6
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
6
ROLES AND TASK PER PARTNER | 
INAPP | Cooperation in the work out of the Project Monitoring Evaluation Plan and related tools (format). Cooperation in the outcomes analysis and Validation of Interim and Final Reports planned (EN).
ALL PARTNERS | Validation of Monitoring/evaluation Plan, realisation of all tasks concerned with the evaluation/monitoring actions, with respect to timings, procedure and format foreseen in the Plan.
Notes: Activity 1.1: profiling of ‘low-skilled individuals’ and relevant sub-categories
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk research activity for the identification of adequate indicators to identify “low-skilled” taking stock of existing literature and PIAAC measurements in order to outline sub-categories of low-skilled individual among those showing similar characteristics by their socio-economic status (e.g. sex, age, income, location, nationality, educational attainment etc.). In doing so, INAPP will liaise with the co-applicant regions to fine-tune their findings.
Activity 1.2: Mapping of existing policies, measures and resources
Target groups: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk/Field analysis to draw an overview of existing policies and tools. Information will be collected covering the following: policies, measures, stakeholders and resources which are relevant for the UP development, having in mind all sub-groups of low-skilled defined in activity 1.1. This activity will build upon and update existing analysis carried out in Italy by the National coordinator for adult learning (INAPP), namely on mapping stakeholders for the governance of adult learning at the national and regional level both from public and private sector organisations. In the same line, there is a need to update the work carried out on available funding instruments for adult learning and their potential synergies, so as to quantify relevant resources for the implementation of the UP and, above all, seek ways to make them fully available . This will be further integrated with information from territorial partners. For example, consideration will be given to issues such as how to exploit flexibility in the regional and national ESF programming to better support the implementation of the UP. An assessment will also be made of the amount of funding already spent /still available, so to inform relevant stakeholders on existing funding opportunities. Recommendations will be also developed that will suggest ways for multi-level stakeholders to share information, best practices and tools, so as to increase coordination and effectiveness of the governance. The mapping exercise will also present suggestions on how to exploit to the fullest available tools and resources. Partners are aware of the need to build upon the work already
Activity 1.3: Rapid assessment of European policies and best practices and benchmarking analysis with the case of France
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M2, Italy and France
- Short description: Literature review/Appraisal of EU-level tools and instruments facilitating the implementation of UP. Comparative analysis French system, to maximise spill-overs and by virtue of the expertise of CEREQ in this field, providing a report of desired features that a model for the implementation of the UP should include
Activity 1.4: Launch event of the action
Target group: National and regional authorities and socio-economic partners in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1, Italy (Rome)
Short description:
The aim of this activity is to inform all key actors of the UP about the aim and content of the action so as to ensure their active involvement since the early stages of the project, agree on information needs and fine tune the scope of the action in line with their needs and suggestions. The activity will take the form of a ½ day stakeholders’ workshop and will be hosted by INAPP.

## Slide 7
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
7
METHODS | AIM | TOOLS | HOW AND WHEN
Desk analysis | Monitoring workplan activities - and related outputs - work in progress | Questionnaires | Delivering by e-mail every 4 months
Interviews to main actors of implementation process | Completing or deepening desk analysis results | Interview grids | Direct or Indirect, if necessary
Budget flow analysis | Monitoring project expenses (cash flow) | Format tool designed with reference to the format/tools provided by CE | Delivering by e-mail every 5 months
Notes: Activity 1.1: profiling of ‘low-skilled individuals’ and relevant sub-categories
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk research activity for the identification of adequate indicators to identify “low-skilled” taking stock of existing literature and PIAAC measurements in order to outline sub-categories of low-skilled individual among those showing similar characteristics by their socio-economic status (e.g. sex, age, income, location, nationality, educational attainment etc.). In doing so, INAPP will liaise with the co-applicant regions to fine-tune their findings.
Activity 1.2: Mapping of existing policies, measures and resources
Target groups: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk/Field analysis to draw an overview of existing policies and tools. Information will be collected covering the following: policies, measures, stakeholders and resources which are relevant for the UP development, having in mind all sub-groups of low-skilled defined in activity 1.1. This activity will build upon and update existing analysis carried out in Italy by the National coordinator for adult learning (INAPP), namely on mapping stakeholders for the governance of adult learning at the national and regional level both from public and private sector organisations. In the same line, there is a need to update the work carried out on available funding instruments for adult learning and their potential synergies, so as to quantify relevant resources for the implementation of the UP and, above all, seek ways to make them fully available . This will be further integrated with information from territorial partners. For example, consideration will be given to issues such as how to exploit flexibility in the regional and national ESF programming to better support the implementation of the UP. An assessment will also be made of the amount of funding already spent /still available, so to inform relevant stakeholders on existing funding opportunities. Recommendations will be also developed that will suggest ways for multi-level stakeholders to share information, best practices and tools, so as to increase coordination and effectiveness of the governance. The mapping exercise will also present suggestions on how to exploit to the fullest available tools and resources. Partners are aware of the need to build upon the work already
Activity 1.3: Rapid assessment of European policies and best practices and benchmarking analysis with the case of France
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M2, Italy and France
- Short description: Literature review/Appraisal of EU-level tools and instruments facilitating the implementation of UP. Comparative analysis French system, to maximise spill-overs and by virtue of the expertise of CEREQ in this field, providing a report of desired features that a model for the implementation of the UP should include
Activity 1.4: Launch event of the action
Target group: National and regional authorities and socio-economic partners in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1, Italy (Rome)
Short description:
The aim of this activity is to inform all key actors of the UP about the aim and content of the action so as to ensure their active involvement since the early stages of the project, agree on information needs and fine tune the scope of the action in line with their needs and suggestions. The activity will take the form of a ½ day stakeholders’ workshop and will be hosted by INAPP.

## Slide 8
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
8
WHAT IS TO BE PERIODICALLY CHECKED?
Activities planned for each Work Package of the Workprogramme approved
Outputs production and planning
Dissemination and valorisation of outcomes/outputs
Timings and deadlines
Human and financial resources implied
All these aspects must be monitored using specific tools and respecting fixed timings.

## Slide 9
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
9
Leader of the Monitoring and Evaluation is INAPP
INAPP will be in charge of:
drafting a detailed Monitoring and Evaluation Plan (monitoring procedure and strategy consistently with the project workprogramme, including timings, formats, etc.);
providing the formats of all tools necessary to implement the monitoring actions planned (questionnaires and grids);
delivering the monitoring tools to all partners consistently with the monitoring deadlines planned;
analysing the monitoring outcomes and reporting on the results;
producing monitoring reports (Interim and Final) and 1 Final Report
Notes: Activity 1.1: profiling of ‘low-skilled individuals’ and relevant sub-categories
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk research activity for the identification of adequate indicators to identify “low-skilled” taking stock of existing literature and PIAAC measurements in order to outline sub-categories of low-skilled individual among those showing similar characteristics by their socio-economic status (e.g. sex, age, income, location, nationality, educational attainment etc.). In doing so, INAPP will liaise with the co-applicant regions to fine-tune their findings.
Activity 1.2: Mapping of existing policies, measures and resources
Target groups: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk/Field analysis to draw an overview of existing policies and tools. Information will be collected covering the following: policies, measures, stakeholders and resources which are relevant for the UP development, having in mind all sub-groups of low-skilled defined in activity 1.1. This activity will build upon and update existing analysis carried out in Italy by the National coordinator for adult learning (INAPP), namely on mapping stakeholders for the governance of adult learning at the national and regional level both from public and private sector organisations. In the same line, there is a need to update the work carried out on available funding instruments for adult learning and their potential synergies, so as to quantify relevant resources for the implementation of the UP and, above all, seek ways to make them fully available . This will be further integrated with information from territorial partners. For example, consideration will be given to issues such as how to exploit flexibility in the regional and national ESF programming to better support the implementation of the UP. An assessment will also be made of the amount of funding already spent /still available, so to inform relevant stakeholders on existing funding opportunities. Recommendations will be also developed that will suggest ways for multi-level stakeholders to share information, best practices and tools, so as to increase coordination and effectiveness of the governance. The mapping exercise will also present suggestions on how to exploit to the fullest available tools and resources. Partners are aware of the need to build upon the work already
Activity 1.3: Rapid assessment of European policies and best practices and benchmarking analysis with the case of France
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M2, Italy and France
- Short description: Literature review/Appraisal of EU-level tools and instruments facilitating the implementation of UP. Comparative analysis French system, to maximise spill-overs and by virtue of the expertise of CEREQ in this field, providing a report of desired features that a model for the implementation of the UP should include
Activity 1.4: Launch event of the action
Target group: National and regional authorities and socio-economic partners in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1, Italy (Rome)
Short description:
The aim of this activity is to inform all key actors of the UP about the aim and content of the action so as to ensure their active involvement since the early stages of the project, agree on information needs and fine tune the scope of the action in line with their needs and suggestions. The activity will take the form of a ½ day stakeholders’ workshop and will be hosted by INAPP.

## Slide 10
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
10
All project partners are in charge of:
identifying a contact person responsible of communicating all data and information requested;
using the formats (questionnaires) provided;
providing accurate information;
filling all sections foreseen in the formats following the indications provided;
respecting timings and deadlines provided.

## Slide 11
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
11
The monitoring will be realised mainly through a desk analysis action, using semi-structured grids that will be sent to all partners, by e-mail, around every 4 months. All partners will be requested to fill in the grid and send it back respecting the deadlines provided.
The aim will be the one of detecting the work in progress of:
Specific activities or actions
Outputs realisation
Dissemination outputs and outcomes
Beneficiaries’ feedback
Timings foreseen
Budget spent
Every grid will refer to a specific Work Package of the workprogramme. The information requested would concern one or more activity included in the WP concerned.
Partners will be also asked to provide some analytical and quality information, in order to provide a kind of self- evaluation of the work done or of the situation approached.
Notes: Activity 1.1: profiling of ‘low-skilled individuals’ and relevant sub-categories
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk research activity for the identification of adequate indicators to identify “low-skilled” taking stock of existing literature and PIAAC measurements in order to outline sub-categories of low-skilled individual among those showing similar characteristics by their socio-economic status (e.g. sex, age, income, location, nationality, educational attainment etc.). In doing so, INAPP will liaise with the co-applicant regions to fine-tune their findings.
Activity 1.2: Mapping of existing policies, measures and resources
Target groups: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk/Field analysis to draw an overview of existing policies and tools. Information will be collected covering the following: policies, measures, stakeholders and resources which are relevant for the UP development, having in mind all sub-groups of low-skilled defined in activity 1.1. This activity will build upon and update existing analysis carried out in Italy by the National coordinator for adult learning (INAPP), namely on mapping stakeholders for the governance of adult learning at the national and regional level both from public and private sector organisations. In the same line, there is a need to update the work carried out on available funding instruments for adult learning and their potential synergies, so as to quantify relevant resources for the implementation of the UP and, above all, seek ways to make them fully available . This will be further integrated with information from territorial partners. For example, consideration will be given to issues such as how to exploit flexibility in the regional and national ESF programming to better support the implementation of the UP. An assessment will also be made of the amount of funding already spent /still available, so to inform relevant stakeholders on existing funding opportunities. Recommendations will be also developed that will suggest ways for multi-level stakeholders to share information, best practices and tools, so as to increase coordination and effectiveness of the governance. The mapping exercise will also present suggestions on how to exploit to the fullest available tools and resources. Partners are aware of the need to build upon the work already
Activity 1.3: Rapid assessment of European policies and best practices and benchmarking analysis with the case of France
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M2, Italy and France
- Short description: Literature review/Appraisal of EU-level tools and instruments facilitating the implementation of UP. Comparative analysis French system, to maximise spill-overs and by virtue of the expertise of CEREQ in this field, providing a report of desired features that a model for the implementation of the UP should include
Activity 1.4: Launch event of the action
Target group: National and regional authorities and socio-economic partners in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1, Italy (Rome)
Short description:
The aim of this activity is to inform all key actors of the UP about the aim and content of the action so as to ensure their active involvement since the early stages of the project, agree on information needs and fine tune the scope of the action in line with their needs and suggestions. The activity will take the form of a ½ day stakeholders’ workshop and will be hosted by INAPP.

## Slide 12
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
12
Description of activities realised: information on process adopted, methodology applied, subjects involved;
Description of possible divergences/difficulties encountered, with respect to planned and realised activities, and reasons related;
Recovery actions or solutions adopted;
Outputs realised or in progress.
A few examples of the K-questions
Notes: Activity 1.1: profiling of ‘low-skilled individuals’ and relevant sub-categories
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk research activity for the identification of adequate indicators to identify “low-skilled” taking stock of existing literature and PIAAC measurements in order to outline sub-categories of low-skilled individual among those showing similar characteristics by their socio-economic status (e.g. sex, age, income, location, nationality, educational attainment etc.). In doing so, INAPP will liaise with the co-applicant regions to fine-tune their findings.
Activity 1.2: Mapping of existing policies, measures and resources
Target groups: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1/M2, Italy
Short description: Desk/Field analysis to draw an overview of existing policies and tools. Information will be collected covering the following: policies, measures, stakeholders and resources which are relevant for the UP development, having in mind all sub-groups of low-skilled defined in activity 1.1. This activity will build upon and update existing analysis carried out in Italy by the National coordinator for adult learning (INAPP), namely on mapping stakeholders for the governance of adult learning at the national and regional level both from public and private sector organisations. In the same line, there is a need to update the work carried out on available funding instruments for adult learning and their potential synergies, so as to quantify relevant resources for the implementation of the UP and, above all, seek ways to make them fully available . This will be further integrated with information from territorial partners. For example, consideration will be given to issues such as how to exploit flexibility in the regional and national ESF programming to better support the implementation of the UP. An assessment will also be made of the amount of funding already spent /still available, so to inform relevant stakeholders on existing funding opportunities. Recommendations will be also developed that will suggest ways for multi-level stakeholders to share information, best practices and tools, so as to increase coordination and effectiveness of the governance. The mapping exercise will also present suggestions on how to exploit to the fullest available tools and resources. Partners are aware of the need to build upon the work already
Activity 1.3: Rapid assessment of European policies and best practices and benchmarking analysis with the case of France
Target group: Stakeholders in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M2, Italy and France
- Short description: Literature review/Appraisal of EU-level tools and instruments facilitating the implementation of UP. Comparative analysis French system, to maximise spill-overs and by virtue of the expertise of CEREQ in this field, providing a report of desired features that a model for the implementation of the UP should include
Activity 1.4: Launch event of the action
Target group: National and regional authorities and socio-economic partners in the field of Adult Learning
Foreseen implementation time, duration and place (if already known): M1, Italy (Rome)
Short description:
The aim of this activity is to inform all key actors of the UP about the aim and content of the action so as to ensure their active involvement since the early stages of the project, agree on information needs and fine tune the scope of the action in line with their needs and suggestions. The activity will take the form of a ½ day stakeholders’ workshop and will be hosted by INAPP.

## Slide 13
E.QU.A.L. Enhancing Qualification of Adult Learners through the implementation of Upskilling pathways
WP 5 - MONITORING/EVALUATION
13
Formats to be used and filled in will be articulated as follows:
Partnership meetings Minute Format
Report on activities (per WP)
Report on Dissemination Activities
Report on beneficiaries’ feedback (transfer and dissemination activities)
Partnership members’ evaluation of partnership meetings
Financial cash flow
Tools Typology (Formats)

## Slide 14
More info on E.QU.A.L. Project
c.vitali @inapp.org
Contact: c.vitali @inapp.org