E.QU.A.L.

Enhancing Qualification of Adult Learners

through the implementation of Upskilling pathways

Agreement N. VS/2018/0016

Monitoring and Evaluation

Plan

(WP 5)

June 2018 - rev.0

Confidential Document (reserved to project partners)

Summary

General Introduction	4

2. E.QU.A.L. project overview	4

2.1 The reason why	4

2.2 E.QU.A.L. Goals	5

2.2.1 Specific objective(s)	5

2.3 The characteristics of the consortium	6

2.4 Structure of the Workprogramme approved	8

3. Structure and principles of E.QU.A.L. Monitoring plan	14

3.1. Methodological framework of the E.QU.A.L. monitoring action	14

3.1.1 Typologies of Project Monitoring	16

3.2 Monitoring Tools	19

3.3 E.QU.A.L. Monitoring Plan	20

3.3.1 Areas/documents of reference	21

3.3.2 Project monitoring process	21

3.3.2.1 Areas under monitoring	22

3.3.2.2 Contents	22

3.3.2.3 Formats	23

3.3.2.4 The Actors	24

4. Structure and principles of E.QU.A.L. Quality Assurance and Evaluation plan	25

4.1 Introduction	25

4.2 Scope	25

4.3 Formative objectives	26

4.4 Summative evaluation (internal audit)	27

4.5 Evaluation Methods	27

4.6 Planning and tools used	29

Allegati	31

ANNEX 1 - Report on activities	31

ANNEX 2 - Report on Dissemination activities	34

ANNEX 3 - Partners' evaluation of Dissemination Seminars	36

ANNEX 4 - Audience evaluation of Dissemination Seminars	39

ANNEX 5 - FINAL REPORT ASSESSMENT SHEET	42

ANNEX 6 – Project timetable	45

# General Introduction

The present document describes the whole of the monitoring and evaluation actions designed for the project E.QU.A.L. to ensure the aims and outcomes achievement, consistently with the work programme approved and to support, if the case, the re-planning of the implementing process, with respect to in itinere decisions, occurrences, obligations and requirements.

Further, it is to be highlighted that the monitoring process is meant to supply the evaluation of interim and final project results by the side of both the partnership members and the European Commission, providing the quantitative and qualitative data and information necessary for the interim and final assessment procedure and for the decision making process.

# 2. E.QU.A.L. project overview

## 2.1 The reason why

Italy remains one of the countries across Europe where the need to up skill is both great and most challenging. In particular:

- the percentage of adults scoring at or below level 1 in literacy in the Survey of Adult Skills (PIAAC) is 27.7%, (19.9% at EU-level), and in numeracy the results are 31.7% and 23.6% respectively. In addition, the percentage of individuals without basic digital skills is 57% of the population aged 16-74, 26 p.p. above the EU average;

- although the participation in education and training of people aged 25-64 increased from 6.2% in 2007 to 7.5% in 2015, the country ranks 15th in the EU and is still below the EU (10.6%) average.

- regarding the share of population with either less than primary or primary and lower secondary education (ISCED levels 0-2) Italy ranks 4th with 40.1%, above both the EU (23.5%) average. Italy has stayed in the same position since 2006, but has improved by 8.6 percentage points (p.p.) since;

- concerning the share of the population with either upper secondary or post-secondary non-tertiary education (ISCED levels 3-4) Italy ranks 18th with 42.3%. This figure is slightly below the EU (46.5%) average, but it does represent an increase in comparison to the 38.4% rate registered in 2006.

Significant policy efforts are being carried out to address this, however:

- there is a continuing need to strengthen employment services capable of promoting upskilling and tailored on individuals’ needs;

- the reform of Provincial Centres for Adult Learning (hereafter PCAL, DPR 263/2012) introduced key innovations that are pertinent to the UP but may need further emphasis towards full implementation;

- there is a need to better address the negative intertwining between fragility in terms of adult skills and high unemployment rates forcing many people out of employment or out of the labour force through labour market relevant upskilling.

## 2.2 E.QU.A.L. Goals

The E.QU.A.L. action will contribute to preparing the ground for the effective implementation of the Upskilling Pathways Recommendation in Italy by providing a concrete contribution in the identification of the main elements of an UP strategy. It will do so by mapping existing policies, tools, and resources following the three-step approach envisaged by the Recommendation (skills assessment, personalized training and skills validation); developing a methodology for the identification of priority groups that can be customized to the needs of the different regional contexts; developing a model for the implementation of the UP building on existing practices. It will work in close cooperation with relevant actors in the field of adult learning and main bodies in charge of the UP strategy in order to ensure that activities and outputs are tailored to their information needs and their awareness is raised. To this end a multi-level and transnational partnership has been developed, involving public and private bodies covering different geographical levels.

Outputs and deliverables will be assessed and disseminated to relevant stakeholders as well as to the general public through a multi-channel communication strategy.

### 2.2.1 Specific objective(s)

The overall objective of the action is to contribute to the upskilling of low skilled adults by supporting relevant Italian national authorities in implementing so called Upskilling pathways in response to the relevant Recommendation of October 2016. In particular the UP recommendation calls on Member States to design and implement schemes characterised by a three-step approach (skills assessment, provision of tailored training and education and validation of acquired skills) aimed at increasing basic numeracy, literacy and digital skills of adults or facilitating the achievement of a higher qualification. To this effect MS are encouraged to submit a national plan of action defining actions and priority group(s) by mid-2018. Based on our knowledge of the Italian governance framework for skills development, we propose to articulate our support as follows: overview of the current situation; identification of criteria for the identification of priority groups; and further support to national and regional stakeholders in devising such upskilling schemes by drawing on existing tools and resources. Our action is characterized by the promotion of a participatory and enabling approach by aiming at maximum dissemination of findings and tools developed throughout the action.

More specifically the action aims at:

- Providing an overview of existing tools and resources upon which UP can be devised and organised, by identifying relevant gaps and weaknesses and proposing ways to overcome them. The overview will be enriched by a transnational benchmarking exercise built around the French experience. The stock-taking action will build upon European Commission and other European institutions analyses and guidelines and the work carried out by the lead applicant in its role as the national coordinator of adult learning, and more in general by capitalising on partners’ unique knowledge and expertise. This objective is fully in line with Specific Objective 1;

- Supporting relevant national authorities as well regional and local partners with the identification of priority groups of Upskilling Pathways, in line with the UP Recommendation. This will be achieved by developing a methodology for the identification of priority groups that can be tailored according to the needs of the different contexts. This objective is in line with Specific Objective 2, calling for provision of support to national authorities in the targeting of UP at priority groups;

- Defining a model for implementing the UP based on the systematization of findings of three regional representative case studies. These are carried out with a view to understanding how existing measures, tools and services may be streamlined and organized so as to support full UP, what works best and other lessons learned. The model will be validated by relevant territorial and national stakeholders with the purpose of testing the adequacy and transferability of the model, the accuracy and usability of the targeting tool and to better gauge its transferability/up scaling. This objective contributes to Specific Objective 1 as it supports competent authorities in taking full stock of the potential for building the UP on the  territories and by providing them with a concrete support tool (model). It also contributes to Specific Objectives 3 in that it contributes to raising their capacity to design and implement UP on their territories.

## 2.3 The characteristics of the consortium

The consortium has been composed according to three criteria:

- institutional (regions and Trento employment agency) and scientific (INAPP and FGB) relevance of the partners involved, which means this proposal ensures high-level expertise both in terms of mapping and analysis as well as in terms of policy implementation and fine-tuning.

- transnational breadth of the proposal, to allow detailed international comparison and ensures spill-overs and mutual learning

- scientific excellence and distinctive understanding of the subject-matter, to maximise quality and efficiency of the analysis and solutions proposed

In particular:

INAPP, lead applicant, is best positioned to develop and implement actions the are fully fit for this call’s purposes, being endowed with unique expertise and knowledge in the field of adult learning in Italy. Most importantly INAPP act as the national coordinator for adult learning for the European Commission and thus plays a key role in ensuring the sustainability of the action. Furthermore, INAPP have already thoroughly analysed the issue of adults upskilling, and, with particular relevance for this proposal they have:

  - carried out an analysis of the working mechanisms of the CPIA’s personalised plans for adult learning, including highlighting possible shortcomings such as the need of better training for staff in the adult learning field;

  - devised, together with an expert group, the regions and the ministry of labour and social policies, the “Atlante del lavoro”, as the main tool for the development of the National Framework of regional qualifications;

  - performed studies and analysis on PIAAC data, having been appointed by the Ministry of Labour and social policy to this, which entails being best positioned to identify target groups.

INAPP will hold the scientific coordination and responsibility of the consortium. In addition it will coordinate WP2 (Targeting), WP3 (modelling -- with territorial partners being co-coordinators), WP5 (M&E) and WP6 (Project management);

REGIONS, main institutional co-applicants, are pivotal to:

  - the provision of qualitative and quantitative information during the ‘tacking stock’ phase at the regional level (skill needs and gaps, existing policies, learning outcomes etc);

  - the development of local upskilling strategies;

  - the shaping of a model for the implementation of the UP;

  - the re-orientation, where feasible, of existing ESF resources; and

more specifically:

  - Lombardy Region bring their best practices in the field of upskilling via dual learning paths and as regards coordination and partnerships among employers, training providers and institutions in charge of upskilling policies.

  - Lazio Region: covers a large territory characterised by a strong duality between metropolitan and rural areas

  - Province of Trento bring their competence in managing a territorial offer of services, which entails meeting the needs of a population living in very different areas (valleys, mountains, cities, cross-border territories) and often bilingual

Given the partnership with key regions as Lombardia, Lazio and Trentino (Labour Agency), this proposal accounts for relevant heterogeneitites in terms of economic structure as well as of characteristics of the services (related to adult learning) offered by each region. Similarly, the proposal can account for heterogeneity in terms of post-crisis response varying across regions and asymmetrically affecting regional Adult learning strategies.

Regions will be responsible for coordinating WP3 tasks in their own territories (case studies, and workshops)

FGB, co-applicant, bring to the consortium their sound expertise in policy advising for the organisation, planning, monitoring and evaluation of active labour market policies and human capital policies. In particular, they:

  - Can provide scientific support in the design of UP interventions, given their expertise in supporting relevant bodies in the provision of Active labour market and social inclusion policies and the knowledge accrued on ‘what works’ in this field; including having carried out, on behalf of CEDEFOP, a service on Governance of EU skills anticipation and matching systems as well as thematic country reviews on apprenticeships which

  - being currently involved in monitoring and evaluation projects on the FEAD and the ESF, can serve as facilitators for mutual learning activities and, with specific respect to the ESF, can leverage on the results of an ongoing study on the contribution of the ESF to the implementation of the NSA and of the Upskilling Pathways Recommendation in particular.

  - can favour the flow of information on the current relevant EU debate;

  - can support and facilitate project management and dissemination activities;

  - can leverage on their expertise in monitoring and evaluation to devise and manage the M&E plan dedicated to this project.

FGB will be responsible for coordinating WP1 (Mapping) and WP4 (Dissemination activities)

CEREQ, French co-applicant, is a key partner for the provision of:

  - International comparison (France as benchmark country for Adult Learning policies)

  - Relevant inputs for the developments of regionally-tailored Adult learning strategies

CGIL, largest labour union in Italy, are key associates in that they:

  - Play an important role in inter-institutional funds for CVET

  - Play a pivotal role in policy-making and advising

  - Act as a contact point on the territory for employment-related needs and could aid guidance and outreach measures

## 2.4 Structure of the Workprogramme approved

E.QU.A.L.Workprogramme is articulated in a total of 6 Workpackages, out of 3 representing cross actions (see figure 1 below):

Figure 1 - Workprogramme approved (18 months)

| WP N. | TITLE | OVERALL DURATION | MAIN ACTIVITIES | MAIN OUTCOMES/OUPUTS |
| --- | --- | --- | --- | --- |
| 1 | Taking stock-Existing adult learning policies, measures and resources | 6 MONTHS | This WP is intended to meet Specific Objective 1 by mapping existing upskilling provisions, stakeholders, tools and resources upon which Upskilling Pathways can be built, building upon partners’ expertise and resources. It will rely on analysis of PIAAC microdata, additional desk and field research and the review of available literature. Furthermore, a specific action will be developed in collaboration with Cereq, in order to widen the perspective of the current provisions within a direct comparative analysis with the French context. The literature review and desk research will cover the national territory, while a more in-depth analysis in involved regional and local territories on specific needs and trends will also be included. The analysis and mapping activities to be carried out in this WP lays the foundations upon which the subsequent WPs will be developed and it will provide the theoretical and conceptual framework of the project. The key elements of this WP are: - mapping and reviewing relevant indicators to identify low-skilled individuals and under-skilling in general, in order to single out vulnerable groups and regional differences among them. - Mapping and reviewing existing policies, measures and resources relevant for the definition and implementation of the UP strategy, in connection with existing qualifications and skills validation frameworks, in line with the low-skilled profiles identified. - Comparative analysis developed in collaboration with Cereq of the existing experiences, tools and best practices in France (i.e. VAE). - Analysing and taking stock of available tools, practices and data at different levels: i) European (gathering information from data different sources, such as the EU Skills Panorama, EPALE and Eurostat), ii) national (National Qualifications Framework and the certification system4, PIAAC and Adult learning); iii) regional levels, focusing on specific relevant practices in the involved partners’ regions. - Investigating ways to increase coherence and coordination among them. The actions of this WP1 build on the expertise in the analysis and implementation of key initiatives in this domain by the E.QU.A.L. partners, such as primarily the analysis carried out by INAPP within the national qualifications framework development (such as the Atlas of Labour and Qualifications5 and the database on Professions, Occupations and Needs6). This is a key strength of the present proposal and will greatly contribute to the achievements of the objectives of the call in Italy. The approach of this WP also takes into account what has already been done in Italy to improve the provision of upskilling services, in terms of legal framework, infrastructures and service organisation. Nevertheless, further efforts in advancing the governance of the system are viewed as key enablers for reaching full effectiveness of the system. |  |
| 2 | Targeting. A model to identify priority groups for the implementation of UP Recommendation in Italy | 6 MONTHS | The objective of this work package is to contribute to meeting the aims of Specific Objective 2, by supporting the national bodies in charge of the implementation of the Upskilling Pathways Recommendation in Italy in the identification of priority groups. Activities will be carried out in parallel to those of WP1, to maximise work efficiency and, above all, providing decision makers with a timely and relevant tool to identify priority groups for the UP. Building upon the analysis developed through WP1, a three-pronged approach will be adopted to come to the actual identification of priority groups: - Elaboration of data and methodology of measurement using PIAAC findings (and other surveys such as ESS for instance) to better define each sub-group of low-skilled individuals and pinpoint those whose needs appear as more pressing; - Identification of labour market relevant skills needs and learning needs at the national and regional level; - Scenario analysis, including social innovation and skills-biased technical change. The main output of this phase is a model which collates quality information on possible target groups of the UP, for the decision makers to avail themselves of a powerful but simple tool for their actual identification. The starting point is the grids developed for WP1, complemented with PIAAC data, labour market needs and a scenario analysis as described above so as to come to a definition of groups that due to various reasons (e.g. lack of sufficient dedicated resources, severe skills gaps, lack of appropriate tools for their upskilling etc.) should be given priority for the implementation of the UP. Activities are based mainly on desk research, but will include field research especially for the identification of labour market skills needs. |  |
| 3 | Modelling: regional case studies for the definition of a model for the implementation of the Upskilling Pathways, including validation | 6 MONTHS | This work package is intended to contribute towards Specific Objective 1 and 3 of the call for proposals, by defining a model for implementing the UP at the regional level and validating it with relevant competent stakeholders at the territorial and national level through the organisation of four dissemination and validation workshops. Three case studies at the regional level will be conducted with a view to understanding how existing measures, tools and services may be streamlined and organised in order to highlight regional features, observing in particular: strengths and weaknesses of existing upskilling pathways, by using as a benchmark the recommendation in the Commission Staff Working Document - Annex I - Tackling low skills: The Skills Guarantee and in comparable relevant literature; - funds to be leveraged on at the regional, national and EU level (e.g. ESF, Erasmus +, AMIF); - priority groups to be addressed, why they are deemed priority and how to effectively reach them. These will be carried out at the regional level through field activities, in close cooperation with local players and relevant regional services and agencies, tacking full stock of the extensive work of mapping and analysis carried out during WP1 and WP2. A SWOT analysis or a comparable tool will set the ground for the definition of a model, which will also give consideration to its transferability/scaling up. This activity will further integrate findings from WP1 on how to increase coherence among existing elements of the UP Recommendation (skills assessments, modular/personalised training, skills certification and their enablers). Once the model has been defined through the comparison of best practices and lessons learned validation activities will be carried out, with the purpose of: - testing the project’s findings against a broader scrutiny also to better gauge the transferability/scaling up of the model as well as the criteria for the selection of target groups; - further disseminate knowledge and build capacity for a larger audience of stakeholders. One workshop will be organised in each region and one at the national level to present the results of the analysis and validate together with the stakeholders its legitimacy, feasibility, anticipate possible weaknesses and ultimately improve it. Such activities are seen as key to enhance capacity within the administration of upskilling services at multiple levels (regional and operator-specific). In this line of reasoning, all stakeholders will be provided with a model to shape their upskilling pathways. |  |
| 4 | Disseminating: multi-channel communication strategy and dissemination activities | 18 MONTHS | This work package contributes to specific objective 3 of this call for proposals, by informing stakeholders on the activities carried out within the action, systematizing and disseminating deliverables and, in so doing, - raising the awareness among relevant stakeholders on the UP and how they can directly contribute to its implementation - improving their capacity to implement UP - ensuring a proactive involvement of relevant actors in the implementation of the action The action adopts a diversified and multi-agent approach to dissemination and awareness raising by envisaging different activities and developing a range of tools based on deliverables of WP1 – 3. Specific objectives of this WP are listed as follows: - Develop tailored dissemination and guidance tools for each WP1 to 3 - Proactively involving relevant stakeholders, line institutions, local authorities, other networks in sharing and discussing project results - Support outreach activities of UP stakeholders. Activities will also include the definition of further outreach tools in close cooperation with relevant stakeholders. As outreach measures should be targeted to the specific challenges that are more germane to each sub-group of low-skilled, an analysis will be carried out to this end also to assess whether to use traditional media campaigns, or awareness raising events e.g. in schools attended by their children/ in local amenities, or to employ more attractive web-based campaigns, social networks etc. This should result in further engagement and cooperation among stakeholders, and ultimately increase awareness also among the low-skilled on the relevance and benefits of upskilling. The latter is particularly significant given the traditional reluctance of adults to engage in further learning. |  |
| 5 | Monitoring and Evaluation | 18 MONTHS | Monitoring and evaluation are a cornerstone of our approach. Monitoring ensures that the project runs according to schedule and that expected outputs and results are on track to be achieved. The project will be assessed in terms of processes and results. Evaluation is constantly fed by Monitoring and assesses whether the project has indeed achieved the expected results, appraises its potential impact and supports the learning process for a better programming of future actions. M&E also respond to transparency and accountability criteria vis à vis the general public, the European Commission and relevant stakeholders M&E are strictly linked with quality assurance, ie those procedures put in place by the action in order to ensure that the project outputs and deliverables are in line with state of the art quality standards. M&E and quality assurance will focus on processes and results. As for the processes, the application of procedures defined in the requirements will be checked with respect for project deadlines. Special attention will be paid to co-operation and consultation with other partners as this guarantees the collaborative nature of the project and the quality of the results achieved. In terms of results, quality assurance will focus on achieving the fixed objectives, in particular their effective implementation, the possibilities for transfer results to similar initiatives/projects, to other countries and communication to target groups. Evaluation is not a separate work stage, but a quality assurance plan which runs through the whole project life cycle.The Quality Assurance Plan will focus on the refinement of procedures, means for verifications and implementation of the main objectives. | Monitoring Interim report (IT) Final Monitoring report (IT) Project Final evaluation report (IT/EN) |
| 6 | Project management. | 18 MONTHS | Project management is designed to ensure a close coordination between partners concerning deadlines, outputs’ structure and contents and organisation of the events. These activities will be ensured by means of constant coordination via mail, skype-meetings and Steering Committee Meetings. The latter will especially recap the activities done and outline arrangements concerning those to come. The Project Coordinator will appoint a project officer who will assist management activities and prepare the ground for the Steering Committee Meetings by recalling partners the envisaged steps according to the description of the action. In any case, any proposal of significant change to the work plan will be communicated to the Commission and, if necessary, object of an official request of amendment. Minor changes will, instead, be discussed and justified by the partnership and duly explained in the Interim and Final Monitoring and Evaluation Reports. In other words, this WP provides for the coordination and scientific supervision of the project, and complements the administrative, financial and reporting aspects of the overall Project Management, to ensure that the diverse strands adopt a common technical-scientific approach that this is consistent with the workplan and goals of the relevant activities. Also PM is strictly related with M&E and Dissemination activities (WP5 and 4 respectively) The WP will be coordinated by INAPP, with the cooperation of all co-applicants. Planning and realisation of a wide range of different tools and channels identified with respect to destination of use, functionality and project work in progress. | PROJECT WEB SITE AND GRAPHIC FORMATS (EN, IT) MULTILINGUAL BROCHURE E.QU.A.L.MAGAZINE - 4 issues from the 5° month, IT/EN, on line in download |

# 3. Structure and principles of E.QU.A.L. Monitoring plan

E.QU.A.L. monitoring action goals are:

- to ensure the conformity and regularity of project activities;

- to verify the achievement of interim and final goals and outcomes expected;

- to highlight the possible divergences between what has been planned and what has been realized;

- to support the identification and adoption of solutions which can properly guarantee the achievement of fixed project objectives.

The presentation of the E.QU.A.L. Plan has been articulated in the following areas and topics:

- Methodological framework of the E.QU.A.L. monitoring action

- Monitoring tools

- E.QU.A.L. Monitoring Plan

## 3.1. Methodological framework of the E.QU.A.L. monitoring action

The methodology chosen refers, first of all, to the EaSI Programme features, to be considered as a general background (particularly: partnership, innovation, sustainability, policy relevance). Within this framework, the project must be necessarily approached as a “whole” and, by consequence, the monitoring action must control and follow the entire project life-cycle, by taking into account the connections between the different components which are activated during its implementation.

Up to the purpose, the partnership decided to focus on the topic of quality and the possible application of quality issues to training/transfer processes, since an expected result can be achieved with greater effectiveness if the related resources and activities are managed as a process.

As a matter of fact, a project can be considered as a place where processes are activated, where “processes” mean the whole of related or interacting activities which turn incoming elements in outgoing elements.

Therefore, a project can be managed and controlled according to a Quality Management System (QMS – see figure 2 below), that is, it can be thought as a place where quality is developed and so it produces phenomena which can be subject to quality control.

The QMS model is based on four main pillars:

- Management responsibility;

- Resource management;

- Product realisation;

- Measurement, analysis and improvement.

By consequence, the model proposed in the following pages, implies the realisation of several actions (to which are related specific expected outcomes) as for example:

- scheduled monitoring surveys on specific themes or components of the Project, by using questionnaires sent via e-mail;

- iterative activities of systematisation of data and information concerning the project;

- drafting of analysis synthetically describing the progress of each project WP;

- elaboration of fiches describing the products/results realised and achieved in general of with respect to each  project WP;

- producing of yearly reports.

As already mentioned, the desk analysis is the main – but not the only -  method that will be applied through the work out and use of questionnaires (semi-structured grids) focused on some relevant issues:

    - Project redefinition or adjustments

    - Partnership management

    - Administrative management

    - Objectives achievement/Products implementation

    - Self-evaluation/Quality Control

    - Dissemination.

In terms of outputs, further to a statistical analysis of the collected data, 2 monitoring reports (Interim - Month 10 and Final – Month 16) will be produced which will represent, with an additional chapter containing a synoptic and synthetic analysis of the results, the source-base for the final internal evaluation report.

### 3.1.1 Typologies of Project Monitoring

In applying the model proposed, have been considered also the different typologies of monitoring implied, since it is necessary to control and check the different dimensions which describe the progress of an intervention. The Plan here proposed answer to the necessity of implementing (see figure 3 below):

- Physical monitoring

- Financial monitoring

- Process monitoring

Figure 3 - Typologies of monitoring

| “Physical” Monitoring | Even if may be difficult to state what “physical data” actually consist of, given the peculiar features of projects, it is possible to say that they are basically: - those concerning the Co-ordinator and the partnership members (beneficiaires) (name, typology of organisation, dimensions of the organisation, country and region, sector of intervention, number of partners and of involved countries); - those concerning the financial resources by project phase and budget heading, on the whole project and in the breakdown per partner as established in the contracts; - those concerning the products (product typology, medium typology, target typology, language, dimensions). |
| --- | --- |
| Financial Monitoring | Referring to the QMS model above mentioned, the financial monitoring is generally implemented in order to: - verify the correct fulfilment of contractual obligations; - support the European Commission decision making as for requests of amendment to the agreement; - supply with an exhaustive picture on how partnerships ensure an effective management of financial, temporal, human and infrastructural resources; - highlight the different coordination styles and communication practices the project management has recourse to in order to support the decision making process. Financial monitoring supports the check of project progress focusing the attention on basic events such as: - agreement deadlines (signature of contracts, submission of Interim and Final Report); - financial flows (between the EC and the Co-ordinator – by checking the reception of the grant instalment – and between the Co-ordinator and its partners -beneficiaries); - potential in itinere changes (budget redefinition by cost heading, redistribution of funds within the partnership). |
| Process Monitoring | E.QU.A.L. will be implemented within the framework of EaSI Programme and, more specifically, within the measure “Awareness-raising activities in Member States on “Upskilling Pathways: New Opportunities for Adults” - Call for proposals VP/2017/011. This process is grounded on the implementation of actions which necessarily ask for the integration and comparison of the different national, regional and sectoral contexts represented by the (transnational) consortium. Therefore, the attention need to be focused on partnership members’ common working paths, which represent the starting point to make the analysis on the qualitative aspects of the project implemented process. In this frame, to monitor the process of the project gives the opportunity to enrich the understanding of project activities with information concerning, for instance: - the relationships, decision making and communication modalities within the partnership; - the partnership capabilities expressed in terms of organisation, identification and solution of problems; - the strategies and channels used to disseminate results; - the evaluation methods. In this case, the related actions must not be limited to verify the variance between planned and realised activities, but they must be based on a participated and active observation of the project processes and of its results (for instance, during the partnership meetings). Such an approach implies the integration of "direct" and “indirect” observation modalities of project processes, aimed at collecting data and information through an analysis of interim and final products/results. Direct observation will be implemented through: - the analysis of partnership project meetings; - the synthesis of all information shared through partnership communication modalities (telephone calls, e-mails, interim or bilateral meetings); - the use of tools aimed at reviewing or re-planning some specific aspects of the project life-cycle, through the iterative and scheduled delivery of questionnaires, while on the other, indirect observation will be aimed at codifying and organising the information concerning the outcomes and outputs related to each workpackage and sub-activitiy. |

## 3.2 Monitoring Tools

Tools to be used to collect information must necessarily be of different kind, not only because of the nature of the phenomena investigated, but also to answer the need of carrying out specific analysis at different stages of the project implementation. These tools should be "user friendly" and adjustable in itinere, they must integrate closed structures - to verify what exists in terms of presence/absence and quantity - and open structures, aimed at highlighting the qualitative/descriptive elements of the process and the possible weaknesses and criticalities encountered. Further, monitoring tools must be articulated in order to meet the complexity of the project and the plurality of elements which needs investigation, but nevertheless they must also be light and easy to be delivered.

Figure 4

| Tool | Sampling criteria WHEN | Quality control area WHAT | Observation |
| --- | --- | --- | --- |
| Project Quality Plan | - | Management Production Evaluation | Indirect |
| Structured questionnaires | periodically | Management Production Evaluation | by e-mail |
| Protocol for carrying out semi-structured face-to-face interviews | - | Management Resources Management Production Evaluation | Direct To be defined, if the case |
| Financial monitoring questionnaires (Excel sheet) | periodically | Resources management Management | by e-mail |
| Grid for meetings observation | To be adopted during meetings planned | Management Resources management | Direct |
| Fiche describing project process | All project’s components two times during the lifecycle of the project | Management Resources Management Production Evaluation | Indirect |

## 3.3 E.QU.A.L. Monitoring Plan

The Monitoring action – implying specific activities and tools - is strictly related to the implementation of a Quality Management System that is requested to be applied to each project approved and that implies the adoption of a range of solutions aimed at ensuring:

- Process transparency

- Sharing of general and specific goals among the actors involved and definition of specific roles and tasks

- Outcomes measurability

- Prevention of non-conformity risks

- Management of variables.

In this frame, the Monitoring Plan is a tool applied within working teams and partnerships with the aim of:

- creating the conditions to continuously verify the project work in progress and the achievement of expected interim and final outcomes, so as:

- to highlight the possible divergences between what has been planned and actually realised;

- to identify the risk areas;

- to adopt the proper measures apt to ensure the achievement of goals defined.

- following and supporting the operative and strategic management of the project itself, in order to make the partnership able to:

- control and evaluate the project quality;

- make eventual changes or adjustments in itinere;

- report to the European Commission (contents and financial issues).

At this purpose, the Plan has been structured so as to implement the regular check of the activities planned – at least the most important ones – and related expenses implied. The macro-areas that will be under control, during the whole life cycle of the project, are:

- Actions and products realised with respect to the ones planned

- Actual implementation timings, with respect to the ones expected

- Financial resources actually spent (cash flows), with respect to the ones available (budget) or foreseen

- Goals and outcomes actually achieved

### 3.3.1 Areas/documents of reference

To work out and implement a Monitoring plan apt to control the conformity between planned and realised, it is first of all necessary to identify both the specific areas and the documents on which this conformity is grounded.

In particular, areas of reference are:

- Budget;

- Timetable;

- Production Process,

and, by consequence, the documents that the partnership must know, take into account and share all along the project life cycle are:

- the proposal approved, where are indicated the general and final goals of the project, direct and indirect beneficiaries, final and interim outcomes and outputs foreseen;

- the project workplan approved, where are provided all detailed information related the actual implementation of the project, step by step;

- the project total budget;

- the detailed budget for each partner involved;

- the Agreement with the Authority financing the intervention (European Commission)

- the Agreements between project Co-ordinator and all Partners (Beneficiaries);

- the administrative and financial procedure ruled by the Programme/Authority financing the intervention, concerning the financial accounting, the activities reporting, the in itinere monitoring and evaluation, etc.

### 3.3.2 Project monitoring process

The Monitoring action is implemented through (see figure 5 following) :

- Periodical Desk analysis (activities and financial resources)

- Interviews to main actors of implementation process (if necessary, to complete or deepen desk analysis results)

- periodical reports on monitoring results

- yearly reports

Fig.5

| METHODS | AIM | TOOLS | HOW AND WHEN |
| --- | --- | --- | --- |
| Desk analysis | To Monitor workplan activities and related outputs work in progress | Questionnaires | Delivering by e-mail every 6 months |
| Interviews to main actors of implementation process | To complete or deepen desk analysis results | Interview grids | Direct or Indirect, if necessary and when necessary |
| Budget flow analysis | To monitor project expenses (cash flow) | Format tool designed with reference to the formats provided by the European Commission | Delivering by e-mail every 4 months |

#### 3.3.2.1 Areas under monitoring

The main areas to be periodically checked are:

- Activities planned for each Work Package of the Workprogramme approved

- Outputs production and planning

- Dissemination and valorisation of outcomes/outputs

- Timings and deadlines

- Human and financial  resources implied

- External evaluation (project beneficiaries' feedback)

All these aspects must be monitored using specific tools and respecting fixed timings.

#### 3.3.2.2 Contents

As above mentioned, the monitoring will be realised mainly through a desk analysis action, using semi-structured grids that will be sent to all partners, by e-mail. All partners will be requested to fill in the grid and send it back respecting the deadlines provided. In particular, the aim will be the one of detecting the work in progress of:

- Specific activities or actions;

- Outputs realisation;

- Dissemination outputs and outcomes;

- Timings foreseen;

- Budget spent.

Every grid sent will refer to a specific Work package of the project workprogramme and the information requested would concern one or more activity included in the work package concerned. In the same grid the partners will be also asked to provide some analytical and quality information, in order to provide a kind of self- evaluation of the work done or of the situation approached.

As an example, the main K-questions would be:

- Description of activities realised: information on process adopted, methodology used, subjects involved;

- Description of possible divergences/difficulties encountered, with respect to planned and realised activities, and reasons related;

- Recovery actions or solutions adopted;

- Outputs realised or in progress.

#### 3.3.2.3 Formats

Formats to be used and filled in will be articulated as follows:

- Partnership meetings Minute Format

- Report on activities

- Report on Dissemination Activities

- Report on beneficiaries evaluation (feedback) of project activities (transfer and dissemination)

- Financial cash flow

All data requested will be necessary also to report on the project work in progress to the EC (Interim and Final Report). Interim and Final Reports, in fact, imply - with respect to the project workprogramme approved - detailed info on:

- project activities realised;

- project outputs;

- project outcomes (quantitative/qualitative impact on targeted national contexts involved in the transfer action);

- dissemination activities realised (implying quantitative/qualitative info on project beneficiaries; typology of tools/actions, samples of tools/materials);

- financial resources spent (detailed info on budget cash flow, consistently with financial and administrative rules of EaSI Programme).

#### 3.3.2.4 The Actors

Referring to the E.QU.A.L. proposal and workprogramme approved and in particular the Workpackage 5 "Monitoring and Evaluation", the partner responsible for the implementation of the monitoring and evaluation activities is INAPP. The action planned is to be meant as "internal" to the partnership and so, the whole of activities and outputs planned will be realised through personnel involved with respect to competences, tasks and responsibilities of each partner.

INAPP will have to indicate one Staff member, that will be in charge of:

- providing a detailed programme (deadlines) of the monitoring procedure, consistently with the project workprogramme re-planning;

- providing the formats of all tools necessary to implement the monitoring actions planned (questionnaires and grids);

- delivering the monitoring tools to all partners consistently with the monitoring deadlines planned;

- analysing the monitoring outcomes and reporting on the results to the project Coordinator;

- producing 3 reports (1 Monitoring Interim report, 1 Final Monitoring Report, 1 Final evaluation report).

On the other side, all project partners (promoter included) will be in charge of:

- identifying a contact person responsible of communicating all data and information requested;

- using the formats (questionnaires) provided by the external expert;

- providing accurate information;

- filling all sections foreseen in the formats following the indications provided;

- respecting timings and deadlines provided.

# 4. Structure and principles of E.QU.A.L. Quality Assurance and Evaluation plan

## 4.1 Introduction

The aim of the Quality Assurance and Evaluation Plan is to deliver clarification and guidance to procedures and criteria used to quantify and qualify the project as a whole and the work packages’ efficiency separately.

The monitoring and evaluation are  tools for partnership support and quality assurance. The philosophy of evaluation is participatory, seeking the active involvement of all stakeholders. The evaluation aims to give guidance to the project partners for possible adjustments in the implementation of tasks.

Quality means:

- Do what you promised (compliance with application)

- Meet the requirements (users’ needs & expectations)

- Fitness for use, not perfection (suitability, usability)

- Everything that can be improved:

  - Evaluate products, outcomes and results

  - Evaluate processes and procedures

## 4.2 Scope

This Quality Management System aims at:

- ensure ongoing progress and achievement of interim and end;

- highlight non-compliance between planned and realized,

- to identify areas of risk measures preventive / corrective allow, therefore, a constant repositioning of the intervention objectives.

The overall structure of this Quality Plan (content, method, tools) will be based on the distinction between:

- Control:

verification of eligibility and conformity implementing the administrative level;

- Monitoring:

comparison iterated the progress of the implementation (process / outputs) than planned, to identify gaps and formulate hypotheses and coping strategies. Criteria and indicators relate to specific operational objectives to be pursued according to the times, methods and resources, data;

- Evaluation:

monitoring the implementation of the project in terms of outputs, results and impacts overall and specific products (groups / target systems) or in contexts that can produce target. Criteria, indicators, parameters and indexes cannot be defined universally and free content, but are determined from the general and specific objectives of the action to be evaluated.

This Quality plan is defined at the start of the project and the final version is agreed upon mutual agreement with the partners.

The aim of quality assurance is:

- ensure the quality, effectiveness and efficiency of the implementation of the project activities.

- ensure the achievement of objectives.

- monitor and Assess the compliance between planned and carried out during the implementation process of the project.

- ensure the constant monitoring and evaluation of the process, the results and the administrative and financial aspects of the project.

- develop and share methods, indicators and parameters for quality control and instruments of detection of quantitative and qualitative data.

## 4.3 Formative objectives

The formative objective is by using the PDCA-circle (E.W. Deming) to monitor the program implementation and results, as a support to continuous improve the products and process.

It gives tangible and objective measures of the performance and uses a set of indicators. They define the target level, which will correspond to the objective of the programme.

- Resource indicators refers to the budget allocated, financial are used to monitor progress of commitments and payments (e.g. Interim financial report)

- Output indicators refers to the activities;

- Result indicators (e.g. evaluation of a meeting)

- Impact indicators refer to the consequences of the project.

## 4.4 Summative evaluation (internal audit)

Previous to the presentation of the interim and final report, an internal audit will check if the main results, recommendations and statistical data obtained during the project, and the main administrative and financial details on the projects’ progress agree with the project requirements.

The output of the summative evaluation is used for Interim reporting to the European Commission and used therefore as guide for final Report.

The  aim of internal assessment is to provide the partnership with internal evaluation tools of its activities and facilitate the partners in controlling and monitoring each step of the project.

Each partner has to fulfill and deliver the following reports, at the end of every trimester. All the documents have to be delivered the Project coordinator.

The reports are:

- Valorisation activity form deals with all valorisation activities e.g.: presentation, conference, publication, information about the project on website, meetings, and others.

- Progress report enumerate the activities carried out by each organization, referring the monitored period.

## 4.5 Evaluation Methods

In the evaluation a mixed method of combining quantitative and qualitative data is used.

Methods are:

| Evaluation method / tool | When/where |
| --- | --- |
| Interviews (in-depth; and by telephone) | during project meetings |
| Desk analysis | project reports, minutes, brochure, e-communication between partners, deliverables |
| Observation | during project meetings, Workshops/Conferences |
| Statistics like: - Number of stakeholder groups per country? - How many persons applied to attend the training? - How many persons participated? - How many persons took part in the national stakeholders meeting? - Target respondents: partners, participants. |  |

In terms of action, it is expected:

- Development plan monitoring and evaluation (M3).

The Plan includes project milestones and associated deliverables. To apply the internal control compliance implementation in progress, in addition to indicating procedures, instruments and specific deadlines are shown documents which partners should refer to 18 months (eg project work plan, budget, timetable and organization, etc.).

- Preparation format detection and quantitative data.

The comparability of data is essential for the efficient communication between the partners and the sharing of work in progress. Therefore expected: format grids and reports / records (measurements of only partner, sharing evaluative information and agreements made); evaluation questionnaires / observation indoor / outdoor (beneficiaries and staff involved); format for detection of periodic cash flows of the project.

- Implementation desk analysis of periodic (semi - M7).

Administration partners to semi-structured grids, to obtain information on specific areas of control: activities carried out, was ongoing activities and timing, results, problems encountered and corrective actions taken. In this way, you can monitor compliance and implementation regularity, and obtain information critical analysis and evaluation.

- Detection of periodic financial resources (semi - M6).

The cash flow is an important aspect to be kept under constant control as it relates to operations and production. The survey is useful for identifying potential losses or reserves which, if not corrected, could adversely affect compliance with the programmed. This recognition is also needed to comply with the financial monitoring procedures required by the same National Agency.

- Development of two reports (interim and final)

where there is evidence of the progress of the project, to be shown any adjustments to be made to the work plan and analyzed in terms of effectiveness, efficiency and relevance, intermediate results and impact (sustainability and transferability) product with respect to the contexts / groups target. The reports include an updated Risk Assessment Chart, to check: budget and products for business or WP, timetable for implementation. The report will be relevant to draft and submit interim and final reports under the Programme.

Other criteria used are the descriptions of the aims and the deliverables as described in the project plan.

## 4.6 Planning and tools used

| Product / activity to be developed or evaluated |  | F=form S=sum |  | Evaluation method / tool |  | Result |
| --- | --- | --- | --- | --- | --- | --- |
| Development plan monitoring and evaluation including - project milestones and associated deliverables. - indicating procedures, instruments and specific deadlines - List of documents which partners should refer to (eg project work plan, budget, timetable and organization, etc.). |  |  |  | Planning monitoring and evaluating |  | Monitoring and evaluation plan (this report) |
| Preparation of formats for - evaluation questionnaires - grids and reports - records (measurements of only partner, sharing evaluative information and agreements made); - observation indoor / outdoor (beneficiaries and staff involved in the transfer) - format for detection of periodic cash flows of the project. |  | Prep |  | Preparation monitoring and evaluating |  | Questionnaires Formats for grids and reports Format for record sheets Formats for observation |
| 1st meeting |  | F |  | Survey questionnaire Observation indoor |  | Internal report |
| 2nd meeting |  | F |  | Survey questionnaire Observation indoor |  | Internal report |
| 3rd meeting |  | F |  | Survey questionnaire Observation indoor |  | Internal report |
| Final conference |  | S |  | Survey questionnaire Observation indoor Interviews |  | Internal report |
| Financial monitoring Financial survey : - identifying potential losses or reserves which could adversely affect compliance with the programmed. - comply with the financial monitoring procedures required by the same National Agency. | S |  | format for detection of periodic cash flows of the project. |  | Concept (M7-M10) Interim report (M11) Final report (M23) |  |
| Summative survey obtain information on specific areas of control: - activities carried out, - problems encountered - corrective actions taken. Goal: monitor compliance and implementation regularity, and obtain information critical analysis and evaluation. |  |  | Questionnaire Interview |  |  |  |

# Allegati

# ANNEX 1 - Report on activities

To be filled in by each partner

PERIOD COVERED BY THE REPORT:   from dd/mm/yyyy  -  to  dd/mm/yyyy

| Work Package N. |  |  |  |
| --- | --- | --- | --- |
| TITLE |  |  |  |
| START DATE | dd/mm/yyyy | END DATE | dd/mm/yyyy |

| REPORT ISSUED BY | Name of Partner |
| --- | --- |
| AUTHOR |  |
| DATE OF ISSUE | dd/mm/yyyy |

- ACTIVITIES REALISED

(please provide a detailed description of the activities implemented, focusing on: process and methodology adopted, subjects involved)

- DEVIATIONS FROM INITIAL PLANNING AND REASONS RELATED

(Referring to point 1 above, please describe in details the difficulties encountered and reasons related)

3. RECOVERY ACTIONS ADOPTED

(Referring to point 2 above, please describe the solutions adopted to overcome difficulties)

4. RESULTS/PRODUCT REALISED OR IN PROGRESS

Please provide a detailed description of all results/products related to the activities realised. For each result/product, please provide the following information:

| Realisation process |  |
| --- | --- |
| Completed  In progress  | estimated percentage(%) of work completed: _% |
| Result/Product Type |  |
| Result/Product language/s |  |
| Medium used (e.g. paper, cd Rom, text, database etc.) |  |
| Findings, conclusions and lessons of evaluation and testing |  |
| Was the result/product/process modified respectively adapted after evaluation and testing? |  |

# ANNEX 2 - Report on Dissemination activities

To be filled in by each partner

All materials produced/used for dissemination activities should be attached to the present format

PERIOD COVERED BY THE REPORT:   from dd/mm/yyyy  -  to  dd/mm/yyyy

| Work Package N. |  |  |  |
| --- | --- | --- | --- |
| TITLE |  |  |  |
| START DATE | dd/mm/yyyy | END DATE | dd/mm/yyyy |

| REPORT ISSUED BY | Name of Partner |
| --- | --- |
| AUTHOR |  |
| DATE OF ISSUE | dd/mm/yyyy |

DISSEMINATION AND EXPLOITATION OF PRODUCTS/RESULTS

Describe clearly and briefly the progress of the activities for the dissemination and exploitation of results filling in the following table.

If possible, refer to each result/product described in Annex 1 point 4.

| No. |  |
| --- | --- |
| Activity description |  |
| Activity start date (dd-mm-yyyy) |  |
| Region |  |
| Targeted sectors |  |
| Targeted groups |  |
| Activity number of participants |  |
| Which institutions/organisations were targeted? |  |
| Organisation type |  |
| Why have these institutions/organisations been chosen, and what is their relevance towards the project objectives? |  |

GENERAL COMMENTS

1. DEVIATIONS FROM INITIAL PLANNING AND REASONS RELATED

2. DESCRIBE THE RESULTS AND FEEDBACK RECEIVED FROM STAKEHOLDERS (TARGET GROUP OR SECTOR) OF IMPLEMENTED DISSEMINATION ACTIVITIES.

# ANNEX 3 - Partners' evaluation of Dissemination Seminars

To be filled in by each partner

| SEMINAR N°: |  |  |  |
| --- | --- | --- | --- |
| PLACE (City): |  | REGION |  |
| COUNTRY: |  |  |  |
| DATE: |  |  |  |

| REPORT ISSUED BY | Name of Partner |
| --- | --- |
| AUTHOR |  |
| DATE OF ISSUE | dd/mm/yyyy |

- Was the Logistics of the Seminar appropriate?

 yes

 no

- Could you please signify your satisfaction degree about the following aspects?

|  | Fully satisfied | Fairly satisfied | Not much satisfied | Unsatisfied |
| --- | --- | --- | --- | --- |
| Clearness of meeting aims |  |  |  |  |
| Exhaustiveness of the documents received |  |  |  |  |
| Clearness of the type of contribution requested to each partner |  |  |  |  |
| Relevance of the Agenda |  |  |  |  |
| Relevance and Quality of speakers’ reports |  |  |  |  |
| Quality of materials distributed |  |  |  |  |
| Level of Interaction achieved with the audience |  |  |  |  |
| Consistency with expectations |  |  |  |  |

- On the whole, how would you describe your attendance to the Seminar?

| Very useful | Fairly useful | Not much useful | Useless |
| --- | --- | --- | --- |

- Advices and suggestions to improve the quality of the following Seminars

# ANNEX 4 - Audience evaluation of Dissemination Seminars

to be filled in by each participant/

“Title of the Seminar”

Date and venue

Dear Sir / Madam,

hereby you will find a short Questionnaire that would help us to assess the quality of the Seminar. Your suggestions will represent an important contribution for the improvement of our next meeting.

We kindly ask you to fill in the Questionnaire and remit it to our staff.

We thank you for your co-operation

The E.QU.A.L. Partnership

| Name |  |
| --- | --- |
| Function |  |
| Organisation |  |
| Field of activity of the Organisation |  |

Do You wish to receive more information concerning the project?

    Yes, by e-mail

Your e-mail:   _________________________________________________

    Yes, by post

Your address: _________________________________________________

- Have you received the invitation in time to organise your participation?

 yes

 no

- Was the Logistics of the Seminar appropriate?

 yes

 no

- Could you please signify your satisfaction degree about the following aspects?

|  | Fully satisfied | Fairly satisfied | Not much satisfied | Unsatisfied |
| --- | --- | --- | --- | --- |
| Clearness of meeting aims |  |  |  |  |
| Exhaustiveness of the documents received |  |  |  |  |
| Clearness of the type of contribution requested to each partner |  |  |  |  |
| Relevance of the Agenda |  |  |  |  |
| Relevance and Quality of speakers’ reports |  |  |  |  |
| Quality of materials distributed |  |  |  |  |
| Level of Interaction achieved with the audience |  |  |  |  |
| Consistency with expectations |  |  |  |  |

- On the whole, how would You describe your attendance to the Seminar?

| Very useful | Fairly useful | Not much useful | Useless |
| --- | --- | --- | --- |

- Referring to Question 4, could You please provide a short  explanation?

- Any advices or suggestions to improve the quality of our following Seminars?

# ANNEX 5 - FINAL REPORT ASSESSMENT SHEET

- Objectives, results and products

- Are all planned project outcomes / results available and are they in accordance with aims and objectives as declared in the original application or as officially amended?

| SCORE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 0 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 |

Please, comment:

- Coherence between work programme and activities carried out to date

- Have the planned activities been implemented in accordance with the project’s work programme as declared in the original application, or as officially amended, and have any variations been adequately justified?

| SCORE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 0 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 |

Please, comment:

- Partnership

- Are there clear indications of a real and effective partnership?

- Are there significant changes in the partnership when compared with the application?

- If so, are such changes justified?

- Management

- How was the project managed?

- Have any variation from original plans been adequately justified?

| SCORE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 0 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 |

Please, comment:

- Financial management

- Is the expenditure appropriate and in line with the approved Work programme?

- Is the expenditure appropriate and in line with the project's activities as described in the Final Report?

- Is the expenditure in line with the level of project's implementation ("best value for money" principle)?

| SCORE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 0 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 |

Please, comment:

- Evaluation and/or quality assurance

- How well was the project's strategy for evaluation implemented?

- Were there significant changes compared to the original application?

| SCORE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 0 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 |

Please, comment:

- Dissemination

- How effectively did the project carry out its plan for dissemination?

- What is the quality of the dissemination activities?

| SCORE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 0 | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 |

Please, comment:

Supplementary information to be submitted

Supplementary information required from the project to allow for a complete Final Report analysis:

OVERALL EVALUATION

Overall comment:

Strong points:

Weak points:

| SCORING SYSTEM |  |  |
| --- | --- | --- |
| Score | Definition | Description of score |
| 0 | No evidence | Fails to include a minimum amount of evidence to enable the criterion to be evaluated |
| 1 or 2 | Very weak | Addresses the criterion but with significant and/or many weaknesses |
| 3 or 4 | Weak | Addresses the criterion but with weaknesses |
| 5 or 6 | Acceptable | Addresses the criterion sufficiently |
| 7 or 8 | Good | Addresses the criterion with some aspects of high quality |
| 9 or 10 | Very good | Addresses the criterion with all aspects of high quality |

# ANNEX 6 – Project timetable

Source: OECD.

European Commission, Summary of the Partnership Agreement for Italy, 2014-2020, 2014. Available at: https://ec.europa.eu/info/sites/info/files/partnership-agreement-italy-summary-oct2014_en.pdf

Italy trails only Malta (56.5%), Portugal, and Spain in this ranking (latest data: 2015).